Subject: RE: Hardening Plan — Dates, NetAssist, and the 1-Hour DC Window

Hi [CTO name],

Quick answers to all three, and yes — the 1-hour DC window is workable.

# Corrected dates

Sorry about the day labels in my earlier note.

- Apr 22 (Wed): DR dress rehearsal — full CIS L1 hardening + reboot on the 8 k3s hosts, ~110 min. This is the stress test for the whole protocol.

- Apr 23 (Thu): post-exercise report. Any item that caused instability on DR gets excluded from the DC tag list.

- Apr 30 (Thu): 1-hour window — MySQL Assessment + Application Deployment + safe-tranche hardening on the DC fleet (see below).

- Future DC window (TBD): the deferred hard part — reboot-required items and kernel networking on k3s / MySQL / RabbitMQ / LIMS hosts, using the Apr 22 protocol.

# NetAssist waiver — just one item

CIS 3.3.1 — “Ensure ip forwarding is disabled” (Ubuntu 24.04 LTS v1.0.0 L1 Server). This is the one that broke k3s on Apr 20.

Justification we’ll submit, scoped to k3s masters and workers only:

“Kubernetes requires net.ipv4.ip_forward=1 on every cluster node — pod traffic crosses the host network namespace through CNI bridge and veth interfaces, and with forwarding off the kernel drops those packets. That breaks pod-to-pod, Service ClusterIP, and NodePort, which is exactly what we saw on 20 April 2026. Kubernetes nodes are routers for container traffic by design; CIS 3.3.1 is written for hosts that aren’t routers, so it’s technically incompatible with this role.

Mitigations in place: CNI FORWARD-chain rules scoped to the pod network, kube-proxy DNAT for Service/NodePort translation, k3s nodes sit on the internal management network with external ingress behind upstream load balancers, and ip_forward is reset to 0 on any host repurposed off the cluster. Scope: k3s master and worker nodes only. All other hosts stay in scope for CIS 3.3.1.”

On top of the waiver we’re also pre-staging a sysctl override on every k3s node before hardening runs — so if the NetAssist paperwork drags, the cluster still stays up. CIS 3.3.7 (reverse path filtering) is a known compatibility risk too; we’ll validate it on Apr 22 and flag a second waiver only if it actually fails.

# Apr 30 — yes, DC hardening fits in the 1-hour window

Rather than running the full role, we’ll apply a “safe tranche” across all ~26 DC hosts in parallel — zero downtime, no reboot. The tag list is locked down from the Apr 22 DR rehearsal: anything that caused instability in DR gets excluded before we touch DC.

What’s in: SSH hardening (banner, timeout, MaxAuthTries), password policy, faillock, file permissions, auditd rules, rsyslog/journald config, AIDE, disabling unused filesystem modules, non-network sysctls (ASLR, core dumps, kexec_load_disabled).

What we skip (deferred to a dedicated reboot window): kernel networking (CIS 3.3.x), host firewall enablement (CIS 4.x — ufw/nftables), anything requiring reboot, mount option changes (/tmp noexec, etc.), crypto policy tightening, aggressive SSH cipher/MAC restriction, and anything that could break the Ansible service account mid-run.

Rough sequence for the 1-hour window:

- 0–5 min — Proxmox snapshots

- 5–15 min — Ansible safe-tranche apply (parallel)

- 15–30 min — MySQL Assessment improvements

- 30–45 min — Application Deployment

- 45–55 min — Compliance re-scan + validation

- 55–60 min — Buffer

Expected outcome: safe-tranche items typically close 40+ failures across SSH / filesystem / auditd / logging alone, so your 201 passed / 50 failed target is realistic. I’ll bring the named tag list and expected pass-count delta after the Apr 22 rehearsal for your sign-off before Apr 30.

# Future DC reboot window — aligned with Hugh

When we eventually do the deferred hard part (kernel networking + reboot on k3s / DB / RabbitMQ / LIMS hosts), parallel reboot per tier works, with four guardrails:

- Preflight gate blocks reboot if any k3s node fails the kernel-setting check. Hard fail, no override.

- Proxmox snapshots before the window.

- k3s masters rebooted in pairs to keep etcd quorum; workers and non-k3s tiers parallel per Hugh’s plan.

- Post-reboot smoke test: DNS from a test pod + LIMS login.

# My action items

- Before Apr 22: pre-stage k3s overrides, finalize preflight gate, snapshots, submit CIS 3.3.1 waiver to NetAssist.

- Apr 22 / 23: DR rehearsal + post-exercise report with the finalized safe-tranche tag list for DC.

- Before Apr 30: named tag list and expected pass-count delta for your sign-off.

- Before the future DC reboot window: inventory audit for any DC k3s nodes, extend the CIS 3.3.1 waiver if needed, formal tranche plan with named host lists for approval.

Happy to jump on a call if easier.

Best,

Zul