## Timeline
CIS L1 Server Hardening — Engineering Timeline (2 weeks)
Start: Monday, 20 April 2026 ¦ End: Friday, 01 May 2026 ¦ Scope: configuration-layer hardening + SCAP scan + vendor report
Day | Date | Week | Phase | Task | Target | Effort (hrs) | Dependency | Deliverable
1 | Mon 20 Apr | Week 1 | Canary wrap-up | Complete SCAP scan on .52 (Ubuntu 22.04 canary) | 172.16.102.52 | 3 | - | Scan report, pass/fail counts
1 | Mon 20 Apr | Week 1 | Canary wrap-up | GitHub repo setup: README, .gitignore, LICENSE, scrub IPs | local | 2 | - | Private repo, first commit pushed
1 | Mon 20 Apr | Week 1 | Canary wrap-up | Update HARDENING_REPORT.md with both canary scan numbers | local | 1 | Both canary scans | Updated report artifact
2 | Tue 21 Apr | Week 1 | DR rollout | Proxmox snapshots for all 16 DR hosts | DR fleet | 1 | - | Snapshot log
2 | Tue 21 Apr | Week 1 | DR rollout | Ansible ping sanity + --check --diff dry-run on DR | DR fleet | 1 | Snapshots done | Dry-run output captured
2 | Tue 21 Apr | Week 1 | DR rollout | Apply site-offline.yml across DR phases 2-7 | DR fleet (16 hosts) | 4 | Dry-run clean | Ansible run logs, failed=0
2 | Tue 21 Apr | Week 1 | DR rollout | SSH reachability + service health spot-checks | DR fleet | 1 | Apply complete | Smoke test log
3 | Wed 22 Apr | Week 1 | DR scan | Replicate oscap + SSG 0.1.80 install on DR (ForceIPv4 apt) | DR fleet | 2 | DR applied | oscap present on all DR hosts
3 | Wed 22 Apr | Week 1 | DR scan | Run SCAP scans across all 16 DR hosts | DR fleet | 3 | oscap installed | 16 × HTML + XML reports
3 | Wed 22 Apr | Week 1 | DR scan | Aggregate DR pass/fail numbers into summary table | local | 2 | DR scans done | DR_SCAN_SUMMARY.csv
4 | Thu 23 Apr | Week 1 | Prod rollout | Proxmox snapshots for Phase 1-3 prod hosts | monitoring, k3s | 1 | CTO go-ahead | Snapshot log
4 | Thu 23 Apr | Week 1 | Prod rollout | Phase 1: monitoring (172.16.102.13) | 1 host | 1 | Snapshots | failed=0, monitoring reachable
4 | Thu 23 Apr | Week 1 | Prod rollout | Phase 2: k3s workers (kubectl drain between hosts) | 3 hosts | 2 | Phase 1 green | All workers hardened, pods Ready
4 | Thu 23 Apr | Week 1 | Prod rollout | Phase 3: k3s masters (check etcd health between hosts) | 3 hosts | 2 | Phase 2 green | All masters hardened, etcd 3/3
4 | Thu 23 Apr | Week 1 | Prod scan | SCAP scan on Phase 1-3 prod hosts | 7 hosts | 2 | Phases 1-3 applied | 7 × scan reports
5 | Fri 24 Apr | Week 1 | Prod rollout | Proxmox snapshots for Phase 4-5 prod hosts | mongo-rabbit, proxysql | 1 | - | Snapshot log
5 | Fri 24 Apr | Week 1 | Prod rollout | Phase 4: mongo+rabbit nodes (one at a time, watch cluster) | 3 hosts | 3 | Snapshots | All 3 hardened, cluster healthy
5 | Fri 24 Apr | Week 1 | Prod rollout | Phase 5: proxysql standby -> VIP test -> active | 2 hosts | 2 | Phase 4 green | Both hardened, VIP reachable
5 | Fri 24 Apr | Week 1 | Prod scan | SCAP scan on Phase 4-5 prod hosts | 5 hosts | 2 | Phases 4-5 applied | 5 × scan reports
6 | Mon 27 Apr | Week 2 | Prod rollout | Proxmox snapshots for Phase 6-7 prod hosts | mysql, haproxy | 1 | - | Snapshot log
6 | Mon 27 Apr | Week 2 | Prod rollout | Phase 6: MySQL InnoDB Cluster — secondaries then primary | 3 hosts | 3 | Snapshots | Cluster ONLINE, all nodes hardened
6 | Mon 27 Apr | Week 2 | Prod rollout | Phase 7: HAProxy BACKUP then MASTER (VIP move verified) | 2 hosts | 2 | Phase 6 green | VIP stable, both hardened
6 | Mon 27 Apr | Week 2 | Prod scan | SCAP scan on Phase 6-7 prod hosts | 5 hosts | 2 | Phases 6-7 applied | 5 × scan reports
7 | Tue 28 Apr | Week 2 | Buffer | Buffer / catchup for any incidents, re-runs, fixes | as needed | 8 | - | Issue log (if any)
8 | Wed 29 Apr | Week 2 | Reporting | Aggregate full-fleet scan numbers (17 or 38 hosts) | local | 3 | All scans complete | FLEET_SCAN_AGGREGATE.csv
8 | Wed 29 Apr | Week 2 | Reporting | Investigate outliers (hosts scoring below peer average) | local | 2 | Aggregate ready | Outlier notes
8 | Wed 29 Apr | Week 2 | Reporting | Draft vendor report: methodology, before/after, appendix | local | 3 | Aggregate ready | VENDOR_REPORT.docx draft v1
9 | Thu 30 Apr | Week 2 | Reporting | Internal CTO review of vendor report | local | 2 | Draft v1 | Review feedback captured
9 | Thu 30 Apr | Week 2 | Reporting | Revise vendor report based on CTO feedback | local | 3 | Review feedback | VENDOR_REPORT.docx v2
9 | Thu 30 Apr | Week 2 | Reporting | Archive all scan XMLs + HTML reports to repo | local | 1 | - | Repo committed and pushed
10 | Fri 01 May | Week 2 | Reporting | Deliver final vendor report + scan artifacts to vendor | vendor | 1 | Report v2 signed off | Email + artifact links
10 | Fri 01 May | Week 2 | Reporting | Closing documentation: re-scan runbook, onboarding notes | local | 3 | - | RUNBOOK.md in repo
10 | Fri 01 May | Week 2 | Reporting | Final retrospective + handoff | local | 2 | - | Retro notes
[5 empty] | TOTAL EFFORT (hrs) | 72

## Gantt
Gantt view — 10 working days (Mon–Fri × 2 weeks)
Task | Phase | D1 Mon 20 | D2 Tue 21 | D3 Wed 22 | D4 Thu 23 | D5 Fri 24 | D6 Mon 27 | D7 Tue 28 | D8 Wed 29 | D9 Thu 30 | D10 Fri 01
Complete SCAP scan on .52 (Ubuntu 22.04 canary) | Canary wrap-up | ■
GitHub repo setup: README, .gitignore, LICENSE, scrub IPs | Canary wrap-up | ■
Update HARDENING_REPORT.md with both canary scan numbers | Canary wrap-up | ■
Proxmox snapshots for all 16 DR hosts | DR rollout |  | ■
Ansible ping sanity + --check --diff dry-run on DR | DR rollout |  | ■
Apply site-offline.yml across DR phases 2-7 | DR rollout |  | ■
SSH reachability + service health spot-checks | DR rollout |  | ■
Replicate oscap + SSG 0.1.80 install on DR (ForceIPv4 apt) | DR scan |  |  | ■
Run SCAP scans across all 16 DR hosts | DR scan |  |  | ■
Aggregate DR pass/fail numbers into summary table | DR scan |  |  | ■
Proxmox snapshots for Phase 1-3 prod hosts | Prod rollout |  |  |  | ■
Phase 1: monitoring (172.16.102.13) | Prod rollout |  |  |  | ■
Phase 2: k3s workers (kubectl drain between hosts) | Prod rollout |  |  |  | ■
Phase 3: k3s masters (check etcd health between hosts) | Prod rollout |  |  |  | ■
SCAP scan on Phase 1-3 prod hosts | Prod scan |  |  |  | ■
Proxmox snapshots for Phase 4-5 prod hosts | Prod rollout |  |  |  |  | ■
Phase 4: mongo+rabbit nodes (one at a time, watch cluster) | Prod rollout |  |  |  |  | ■
Phase 5: proxysql standby -> VIP test -> active | Prod rollout |  |  |  |  | ■
SCAP scan on Phase 4-5 prod hosts | Prod scan |  |  |  |  | ■
Proxmox snapshots for Phase 6-7 prod hosts | Prod rollout | [5 empty] | ■
Phase 6: MySQL InnoDB Cluster — secondaries then primary | Prod rollout | [5 empty] | ■
Phase 7: HAProxy BACKUP then MASTER (VIP move verified) | Prod rollout | [5 empty] | ■
SCAP scan on Phase 6-7 prod hosts | Prod scan | [5 empty] | ■
Buffer / catchup for any incidents, re-runs, fixes | Buffer | [6 empty] | ■
Aggregate full-fleet scan numbers (17 or 38 hosts) | Reporting | [7 empty] | ■
Investigate outliers (hosts scoring below peer average) | Reporting | [7 empty] | ■
Draft vendor report: methodology, before/after, appendix | Reporting | [7 empty] | ■
Internal CTO review of vendor report | Reporting | [8 empty] | ■
Revise vendor report based on CTO feedback | Reporting | [8 empty] | ■
Archive all scan XMLs + HTML reports to repo | Reporting | [8 empty] | ■
Deliver final vendor report + scan artifacts to vendor | Reporting | [9 empty] | ■
Closing documentation: re-scan runbook, onboarding notes | Reporting | [9 empty] | ■
Final retrospective + handoff | Reporting | [9 empty] | ■

## Summary
Project summary
Effort by phase
Phase | Tasks | Effort (hrs) | % of total
Canary wrap-up | 3 | 6 | 8.333%
DR rollout | 4 | 7 | 9.722%
DR scan | 3 | 7 | 9.722%
Prod rollout | 10 | 18 | 25%
Prod scan | 3 | 6 | 8.333%
Reporting | 9 | 20 | 27.78%
Buffer | 1 | 8 | 11.11%
TOTAL | 33 | 72 | 100%
Deliverables
Deliverable | Target day
GitHub repo (private) with Ansible role + inventories | Day 1
HARDENING_REPORT.md updated with canary scan numbers | Day 1
DR scan aggregate CSV | Day 3
All 16 DR hosts hardened, scanned | Day 3
All Ubuntu 24.04 prod hosts hardened + scanned | Day 6
FLEET_SCAN_AGGREGATE.csv | Day 8
VENDOR_REPORT.docx (final, CTO-signed off) | Day 10
RUNBOOK.md for future re-scans and new-host onboarding | Day 10
Risks & mitigations
Risk | Likelihood | Impact | Mitigation
Prod host misbehaves post-apply | Low | Medium | Proxmox snapshot + revert; retry after fix
Vendor disputes SSG vs their content | Medium | Medium | Provide per-control breakdown; offer re-scan with matching content
21 × Ubuntu 22.04 hosts out of scope | Medium | Low | Buffer day on D7 absorbs minor issues; bigger fallout pushes to week 3
apt-dependent controls not applied | High | Low | Explicitly scoped out; deferred to network fix workstream
Reboot-dependent controls not active | High | Low | Noted in vendor report; activated at next kernel patch cycle